## Slide 1: Upgrade of KEK Electron/Positron Linac for the Both SuperKEKB and Light Sources
Kazuro Furukawa
Injector Linac, KEK
<kazuro.furukawa@kek.jp>

## Slide 2: Mission of electron/positron Injector in SuperKEKB
40-times higher Luminosity
  20-times higher collision rate with nano-beam scheme
     Low-emittance even at first turn  Low-emittance beam from Linac
     Shorter storage lifetime
  Twice larger storage beam  Higher beam current from Linac
Linac challenges
  Low emittance e-
    with high-charge RF-gun
  Low emittance e+
    with damping ring
  Higher e+ beam current
    with new capture section
  Emittance preservation
    with precise beam control
  4+1 ring simultaneous injection
Linac Upgrade Overview
Notes: Higher Injection Beam Current
  To Meet the larger stored beam current and shorter beam lifetime in the ring
  4~8-times larger bunch current for electron and positron
  Reconstruction of positron generator, etc
Lower-emittance Injection Beam
  To meet nano-beam scheme in the ring
  Positron with a damping ring
  Electron with a photo-cathode RF gun
  Emittance preservation by alignment and beam instrumentation
Quasi-simultaneous injections into 4 storage rings
  SuperKEKB e–/e+ rings, and light sources of PF and PF-AR
  Improvements to beam instrumentation, low-level RF, controls, timing, etc

## Slide 3: Required injector beam parameters
Stage | KEKB (2010) |  | Phase-I (2016) |  | SuperKEKB (final) | 
Item | e+ | e– | e+ | e– | e+ | e–
Energy | 3.5 GeV | 8.0 GeV | 4.0 GeV | 7.0 GeV | 4.0 GeV | 7.0 GeV
Bunch charge | Primary e-10nC → 1 nC | 1 nC | Primary e- 8nC → 0.4 nC | 1 nC | Primary e-10nC → 4 nC | 5 nC
Norm. Emittance (ge) (mrad) | 2100 | 200 | 2400 | 150 | 100/20 (Hor./Ver.) | 50/20 (Hor./Ver.)
Energy spread | 0.125% | 0.125% | 0.5% | 0.5% | 0.1% | 0.1%
No. of Bunch / Pulse | 2 | 2 | 2 | 2 | 2 | 2
Repetition rate | 50 Hz |  | 25 / 50 Hz |  | 50 Hz | 
Simultaneous top-up injection | 3 rings (KEKB e–/e+, PF) |  | No top-up |  | 4+1 rings (SuperKEKB e–/e+, DR, PF, PF-AR) | 

## Slide 4: Linac Injector Status
Phase-3 (Collision exp.) should not be delayed
Injector construction was delayed about 2 years because of resource availability
Important equipment was postponed until FY2017
  Most of damping-ring related epuipment
  Many of lower-emittance related equipment
    including 30 pulsed focusing magnets, 36 steering magnets, ~13 girders
Minimum of 5 months required to purchase, fabricate, install and test
Supplemental budget in FY2016 is not enough
  Best effort ! (asuming enough budget in FY2017)
  KEKB construction
    Linac shutdown for 9 months in 1997, after many devices were fabricated in 1996

## Slide 5: Possible Rescheduling

## Slide 6: Pulsed magnet installation
30 quads and 36 steerings and ~13 girders will be installed at summer 2017
  1 mH, 330 A, 340 V, 1 ms
  Energy recovery to save power (~75%)
  Can change the magnetic field every pulse (50 Hz)
    To support PPM operation or virtual accelerators
Magnets are ready
Power supply tests were OK
Pulsed power supplies and girders will be mass-produced in 2017

## Slide 7: Pulsed magnet development
Pulsed magnet test stand
  Long-term stability was confirmed
Girders were designed
  Waiting for mass-production
  Ready for Phase-3 specification
Successful beam tests
  25-Hz (50-Hz) switching

## Slide 8: Photo cathode RF gun
Successful HER injection during Phase 1
  For 11 days
  Synch. issues resolved
  Emittance to be improved
Emittance measurement
Bunch profile measurement

## Slide 9: Photo cathode RF gun
Secondary RF gun installation
  Incorporate recommendations from review meetings
  Laser, light guides, cavity, etc
  Installed at the beginning of 2017

## Slide 10
Energy compression
±5%
±1.5%
20% is cut at tail
Collimators in the arc
Damping Ring System Layout
M. Kikuchi
DR layout

## Slide 11: Bucket selection in Phase-2 with DR
Without DR, simply wait up to 5120 x 96 ns ~ 490 μs
  96 ns : highest common frequency between linac – ring
With DR, in order to select arbitrary bucket in MR, have to wait up to ~4.5 ms, even if a bucket in DR was carefully selected
  Power supply can wait only 2 ms, one of only 2798 buckets in 5120 buckets can be selected, may have to change LLRF condition at latter half of linac every pulse
  Can be a big challenge in LLRF precision
ARC
e+ Target
e+ BT (3.5GeV, 0.6nC)
e− Gun
KEKB
Primary e– (3.5GeV, 10nC)
ARC
e+ Target
e+ BT (KEKB: 4GeV, 4nC)
e− Gun
SuperKEKB
Primary e– (3.5GeV, 10nC)
e+ DR (1.1 GeV, 4nC)
96ns
>100ns
>100ns
96ns
DR timing

## Slide 12: Subjects to Consider
Have to consider too many subjects !
Phronesis needed (Greek: Practical wisdom, Ability to understand the Universal Truth)
Nov.
Jan.2018

## Slide 13: Injection for Both Experiments of Light-source and B-factory
Proper operation schedule to meet experimental characteristics of those storage rings
Search for common ground with respect for those experiments
Should find and confirm solutions in gradual changes
Improve the machine using virtual accelerator concept, if applicable

## Slide 14: Pulse-to-pulse modulation
ARC
e– (2.5GeV, 0.2nC)
e− Gun
ARC
e+ Target
e+ (4GeV, 4nC)
e− Gun
PF Injection
SuperKEKB-LER Injection
e– (3.5GeV, 10nC)
ARC
e– (7GeV, 5nC)
e− Gun
SuperKEKB-HER Injection
ARC
e– (6.5GeV, 5nC)
e− Gun
PF-AR Injection
Damping ring
Event-based Control System
Every 20 ms
F.B
F.B
F.B
F.B
F.B
F.B
F.B
F.B
Four PPM virtual accelerators for SuperKEKB project Based on Dual-tier controls with EPICS and event-system Independent parameter sets for each VA (20ms) >200 parameters for equipment controls many more for beam instrumentation maybe with additional PPM VA of stealth beam for measurement

## Slide 15: Summary
Injection into SuperKEKB is a challenge with higher beam charge and lower emittance
Steady progress towards designed injection beam in steps
  Alignment: almost confident on the required precision (0.1-mm local, 0.3-mm global), need to maintain for longer term
  Positron generator: another license test, need discharge analysis
  RF gun: following recommendations at review meetings
Will install all of remaining equipment at summer 2017
Will balance between final beam quality and progressive operation
Will balance between particle physics and photon science
With some Phronesis we may enjoy beam commissioning
Summary

## Slide 16
SuperKEKB
dual rings
Mt. Tsukuba
600m Injector Linac
PF-AR
PF
Thank you
Conference papers at <http://www-linac.kek.jp/linac/>

## Slide 18: KEKB Operation Improvement (base of SuperKEKB)
May.2000
Apr.2003
Dual Bunch e+
Feb.2005
Continuous
Injections
Dec.2008
Crab Cavities and
Simultaneous Injection
Belle/KEK
Keeps world luminosity record 2.1 x 1034
red: beam current (e-, e+)
purple: vacuum (e-, e+)
yellow: luminosity
green: integrated luminosity
Past KEKB