## Slide 1: Recent Status of Electron/Positron Injector Linac
Kazuro Furukawa
for Injector Linac, KEK
Many slides from Y. Enomoto and S. Matsumoto

## Slide 2: Mission of Electron/positron Injector in SuperKEKB
  For 40-times higher luminosity in SuperKEKB collider
  Low emittance & low energy spread injection beam with 4-5 times higher beam current
    New high-current photo-cathode RF gun
    New positron capture section
    Damping ring construction
    Optimized beam optics and correction
    Precise beam orbit control with long-baseline alignment
    Simultaneous top-up injection to DR/HER/LER/PF/PFAR
  Balanced injection for the both photon science and elementary particle physics experiments
Injector Linac Mission
The single injector would behave as multiple injectors to multiple storage rings by the concept of virtual accelerator
Notes: Higher Injection Beam Current
  To Meet the larger stored beam current and shorter beam lifetime in the ring
  4~8-times larger bunch current for electron and positron
  Reconstruction of positron generator, etc
Lower-emittance Injection Beam
  To meet nano-beam scheme in the ring
  Positron with a damping ring
  Electron with a photo-cathode RF gun
  Emittance preservation by alignment and beam instrumentation
Quasi-simultaneous injections into 4 storage rings
  SuperKEKB e–/e+ rings, and light sources of PF and PF-AR
  Improvements to beam instrumentation, low-level RF, controls, timing, etc

## Slide 3: Injector Linac Overview
Injector linac configuration
  Major upgrade items
    Photo-cathode RF-gun for low-emittance e-
    Flux concentrator, LAS structure, solenoids, quads for e+
    Pulsed magnets for adequate beam optics for each beam
    High-precision beam position monitor
    High-precision beamline alignment for low emittance

## Slide 4: Required injector beam parameters
Stage | KEKB (final) |  | Phase-I |  | Phase-II |  | SuperKEKB (final) | 
Beam | e+ | e– | e+ | e– | e+ | e– | e+ | e–
Energy | 3.5 GeV | 8.0 GeV | 4.0 GeV | 7.0 GeV | 4.0 GeV | 7.0 GeV | 4.0 GeV | 7.0 GeV
Stored current | 1.6 A | 1.1 A | 1 A | 1 A | – | – | 3.6 A | 2.6 A
Life time (min.) | 150 | 200 | 100 | 100 | – | – | 6 | 6
Bunch charge (nC) | primary e- 10 → 1 | 1 | primary e- 8 → 0.4 | 1 | 0.5 | 1 | primary e- 10 → 4 | 4
Norm. Emittance (ge) (mrad) | 1400 | 310 | 1000 | 130 | 200/40 (Hor./Ver.) | 150 | 100/15 (Hor./Ver.) | 40/20 (Hor./Ver.)
Energy spread | 0.125% | 0.125% | 0.5% | 0.5% | 0.16% | 0.1% | 0.16% | 0.07%
Bunch / Pulse | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Repetition rate | 50 Hz |  | 25 Hz |  | 25 Hz |  | 50 Hz | 
Simultaneous top-up injection (PPM) | 3 rings (LER, HER, PF) |  | No top-up |  | Eventually |  | 4+1 rings (LER, HER, DR, PF, PF-AR) | 
Linac Beam Property Requirements

## Slide 5: Linac Schedule Overview as of Feb.2018
RF-Gun e- beam
commissioning
at A,B-sector
e- commiss.
at A,B,R,C,1
e+ commiss.
at 1,2 sector (FC, DCS, Qe- 50%)
e- commiss.
at 1,2,3,4,5 sector
non damped e+ commiss.
at 1,2, 3,4,5 sectors
e- commiss. at A→5 sectors
damped e+ commiss.
at 1→5 Qe+ = 1~4nC
e- commiss.
at A→5 Qe- = 1~4nC
: Electron
: Positron
: Low current electron
1 - 2 nC
Phase2
1 nC
Phase1
Location
↓
Time →
Phase1: high emittance beam for vacuum scrub
Phase2,3: low emittance beam for collision
New Schedule
Without Top-up
2 - 4 nC
Phase3
Improved RF gun
Direct PF-AR BT
DR Commiss.
Beam Licenses in steps
Low Emittance Beams
4+1 Ring
Injections
Low Emittance Injections

## Slide 6: Newly Installed Pulsed Magnets
A | B | C | 1 | 2 | 3 | 4 | 5
Beam energy
Sector
Positron common optics
with some steering magnets
Independent beam optics
with pulsed magnets
HER (7 GeV)
LER (4 GeV)
PF-AR (6.5 GeV)
PF (2.5 GeV)
Independent beam optics with
26 Quads and 26 Correctors
in Sectors 3 – 5
10 Correctors in Sectors 1 and 2
2 Quads for Positron Target
Common optics was enough
KEKB
SuperKEKB

## Slide 7: Pulsed Magnet Installation 1
Installation during long shutdown at summer 2017
  Not possible before Phase 1 without DR because of the aperture
  Replacement for 64 magnets
  In 99 days between May and October
  All components including magnets, girders, cabling, cooling water, controls, etc.
  In parallel with other replacements and installations
2017/3/31 by N.Toge

## Slide 8: Pulsed Magnet Installation 2
13 New girders
  each for 2 quads and 2 correctors
  ready for 10 μm alignment to realize low emittance preservation in Phase 3

## Slide 9: Pulsed Magnet Installation 3
Standard cabinet configuration for pulsed magnets
4 quads and 4 correctors for a half sector
Controls
Pulsed power supplies & Interlock system
for 2 quads and 2 correctors
Pulsed power supplies & Interlock system
for 2 quads and 2 correctors
Girder and magnet replacements before July
Power supply installation and cabling before September
Comprehensive system tests in September for a month

## Slide 10: Performance of Quad Power Supply
High performance with energy recovery
  Total energy recovery rate of 68.5％ (measured)
  No need for additional wall power (only 39kW for all new magnets)
High precision and high stability by analog feedback with IGBT
  Stability of 0.01％ for 24 hours
Flexible synchronous controls with global event control system
  Independent pulse-by-pulse modulation at 50 Hz
Drives a 1 mH coil at 330 A, 340 V, 1.5 ms risetime

## Slide 11: Power Consumption Measurement
Chart: Quad (50 Hz, 300 A) x 1
| Pjoule-mag | Pjoule-cable | PL | Ptotal | Pmeasured
Q (50 Hz, 300 A) x 1 | 76 | 302.6 | 2250 | 2628.6 | 827
Energy stored in coil inductance
Heat loss on cables
Heat loss at Magnet
Total Energy
Actual power consumption (measured)
Energy recovery ratio = 1 - Pmeasured / Ptotal = 68.5 %

## Slide 12: Stability of Quad Power Supply
0.014578 A / 165.946 A = 0.0107% / 24 hours (for PF_52_4 magnet)
25 mA / div

## Slide 13: New Pulsed Magnets enabled Simultaneous PF/PF-AR Injections And 2 Test Beam Accelerations

## Slide 14: For Phase 3
Pulsed bending magnet addition for switching between RF electron gun / thermal electron gun
Pulsed corrector additions for offset injection (orbit control) to enable lower emittance
40 magnet replacements if budget allows

## Slide 15: Planning Pulsed Bend for Merger Line
HER
LER (primary e– for e+）
PF-AR
PF
Thermionic Gun
Photo RF Gun
24-degree Merger Bend x2

## Slide 16: DR LTR / RTL Waveguides
Accelerating structures for energy / bunch compressors on DR LTR / RTL beam lines
45-m waveguides from linac gallery
Fabrication errors of ~150 μm were found (while schematics from KEK and from maker were correct)
RTL
Linac
DR

## Slide 17: DR LTR / RTL Waveguides
Bunch Compressor on RTL
Energy Compressor on LTR
Components with Red circles had to be replaced

## Slide 18: Structure of Waveguide Flange
RF Contactor (Electric)
Metal Seal (Vacuum)
Correct
Wrong
Emphasized figures
only 150 μm difference

## Slide 19: Fabrication Error and Recovery
September 2017
  A large reflection was observed from the middle of waveguides in the low-power test
  Fabrication errors in 58 waveguide flanges were identified
October 2017
  High power test was performed at a test stand
    Discharge at the gap prevents the power only up to 10% of the nominal power
All 29 wrong waveguides were replaced; some were replaced with the ones with different length, others were newly fabricated

## Slide 20: Fabrication Recovery
Early October 2017
  Removal of all erroneous waveguides from the tunnel
Till November 2017
  Fabrication, preparation and test of replacement waveguides
Late November – early December 2017
  Re-installation in between linac operation
December 17 and 24, 2017
  High-power verification of whole system in between DR construction
January 2018
  Intermittent RF conditioning in between DR construction
  Reached nominal power for Phase 2 and 3 operation
  Confirmed the designed energy compression of one third on LTR

## Slide 21: LTR/ECS – RTL/BCS Waveguide Conditioning

## Slide 22: Summary
New Pulsed Magnets
  Successful fabrication and installation of home-grown low-cost pulsed magnet system during 2017 summer shutdown
  1-month test was performed as scheduled
  Experienced no large troubles so far and enabled stable simultaneous accelerations with different energy beams
Erroneous Waveguides
  Replacements of 29 waveguides were performed successfully even during light source operation and SuperKEKB commissioning /construction
  Achieved the designed energy compression without any harmful impact against DR commissioning
Injector is ready for Phase-2 commissioning

## Slide 23: Thank you