## Slide 1: Present Status of Injector Linac and Damping Ring
Kazuro Furukawa
for injector linac and damping ring, KEK

## Slide 2: Mission of electron/positron Injector Complex in SuperKEKB
40-times higher Luminosity
  20-times higher collision rate with nano-beam scheme
     Low-emittance even at first turn  Low-emittance beam from Injector
     Shorter storage lifetime
  Twice larger storage beam  Higher beam current from Injector
Injector challenges
  Low emittance e-
    with high-charge RF-gun
  Low emittance e+
    with damping ring
  Higher e+ beam current
    with new capture section and BTs
  Emittance preservation
    with precise alignment & beam control
  4+1 ring simultaneous injection
Linac upgrade overview
Notes: Higher Injection Beam Current
  To Meet the larger stored beam current and shorter beam lifetime in the ring
  4~8-times larger bunch current for electron and positron
  Reconstruction of positron generator, etc
Lower-emittance Injection Beam
  To meet nano-beam scheme in the ring
  Positron with a damping ring
  Electron with a photo-cathode RF gun
  Emittance preservation by alignment and beam instrumentation
Quasi-simultaneous injections into 4 storage rings
  SuperKEKB e–/e+ rings, and light sources of PF and PF-AR
  Improvements to beam instrumentation, low-level RF, controls, timing, etc

## Slide 3: Required injector beam parameters
Stage | KEKB (final) |  | Present Phase-I |  | SuperKEKB (final) | 
Beam | e+ | e– | e+ | e– | e+ | e–
Energy | 3.5 GeV | 8.0 GeV | 4.0 GeV | 7.0 GeV | 4.0 GeV | 7.0 GeV
Stored current | 1.6 A | 1.1 A | 1 A | 1 A | 3.6 A | 2.6 A
Life time | 150 min. | 200 min. | 100 min. | 100 min. | 6 min. | 6 min.
Bunch charge | Primary e-10nC → 1 nC | 1 nC | Primary e- 8nC → 0.4 nC | 1 nC | Primary e-10nC → 4 nC | 5 nC
Norm. Emittance (ge) (mrad) | 2100 | 200 | 2400 | 150 | 100/20 (Hor./Ver.) | 50/20 (Hor./Ver.)
Energy spread | 0.125% | 0.125% | 0.5% | 0.5% | 0.1% | 0.1%
No. of Bunch / Pulse | 2 | 2 | 2 | 2 | 2 | 2
Repetition rate | 50 Hz |  | 25 / 50 Hz |  | 50 Hz | 
Simultaneous top-up injection (PPM) | 3 rings (KEKB e–/e+, PF) |  | No top-up |  | 4+1 rings (SuperKEKB e–/e+, DR, PF, PF-AR) | 

## Slide 4: Progress
2010: Beam design and hardware developments
2011-2014: Recovery from earthquake, mainly because of soft-structure girder design
2012-: Linac construction and commissioning
2012-: Step-by-step acquirement of beam licenses
2016: Phase-1
2017: Damping ring commissioning, Phase-2
Continuous: Light source injections
…

## Slide 5: Linac Upgrade Progress towards SuperKEKB (1)
High-charge low-emittance RF gun development
  QTWSC cavity and Ir5Ce photo cathode developments
  Laser development is underway
Positron generator commissioning
  Good agreement with the simulation results
  Will solve discharge issues
Precise alignment for emittance preservation
  Recovering after large earthquake in 2011
  Reaching specification of 0.1~0.3mm
  Longer term stability should be solved
Utility upgrade during FY2014
  for electricity (+1.5MW) and cooling water (+1400L/min)
Ir5Ce Cathode
Quasi traveling wave side couple cavity
Positron generator
Linac Upgrade Overview

## Slide 6: Linac Upgrade Progress towards SuperKEKB (2)
High-power microwave modulator upgrades
Low-level RF controls/monitor upgrades
  Pulse-to-pulse modulation (PPM) between 4+1 rings
  More spaces for increased number of devices
Beam instrumentation
  Large/small aperture beam position monitors (BPM)
  Precise/fast and synchronized BPM readout system
  Wire scanners and beam loss monitors
  Streak cameras
  (Deflectors, etc.)
Pulsed magnet developments
  ~3 bends, ~30 quads, ~40 steerings
  Even with energy recovery
Event-based control and timing system upgrades
  Combination of MRF & SINAP modules
  Essential for PPM operation
  Precise timing & synchronized controls
  Bucket selection at DR and MR
SINAP event modules
Linac Upgrade Overview
Beam wire scanner
Pulse magnet tests

## Slide 7: FC test stand (2015 July)
test operation performed with
  spare FC-base (#4)
  12-kA pulse modulator
  new coaxial cables
  new triplate feeder line
  snubber circuit
  but w/o bridge coils
full-spec (12 kA) operation for continuous 200 hours achieved with no serious breakdowns and problems
FC-base (#4)
triplate
feeder line
snubber
circuit
coaxial
cables
cable connection
inside modulator

## Slide 8: FC assembly #2 & test stand
Operation test with BC field is essential.
FC assembly #1 is radio-activated in the beam line.
Construct assembly #2 for operation with BC field at test stand.
Test-1: operation with FC-head #4 (not work-hardened model) to see what happens in the same situation as the damaged FC. [2016 June, soon]
Test-2: operation with FC-head #5 (well work-hardened model) to check the operability at full current (12 kA) under the BC field. [2016 August ~]

## Slide 9
Energy compression
±5%
±1.5%
20% is cut at tail
Collimators in the arc
Damping Ring System Layout
M. Kikuchi
DR layout

## Slide 10
Damping Ring Beam Parameters
DR
LTR
RTL
Linac
M. Kikuchi
DR layout

## Slide 11
DR
  Magnet: Installation completed (except for steerings in the straight)
  Vacuum chamber: installation is underway
LTR / RTL beam transport lines
  Magnet: Installation completed
  vac. chamber:
    installation, beam instrumentation in 2016 / 2017
  Power supplies for the magnets:
    All delivered. Tuning will be done in 2017.
    Steering PS will be delivered in 2017.
Extraction
line
Damping
Ring
DR and the extraction line
Installation of vac. chambers
Hardware Status
M. Kikuchi
DR construction

## Slide 12
  Beam instrumentation:
    Most of sensors, electronics and cables delivered.
    Cabling of BPM completed in FY2015.
  Kicker system for injection/extraction:
    Magnets and the power supplies are delivered.
Pulse shape of the kickers.
  Septum magnets for injection/extraction:
    Magnets and pulsers are delivered.
Septum magnet for injection.
    Double half-sine pulse for the two bunches
    No ringing after pulse
M. Kikuchi
  Two RF cavities were fabricated.
    installed in the tunnel in June 2016.
DR construction

## Slide 13: Bucket selection in Phase-2 with DR
Without DR, simply wait up to 5120 x 96 ns ~ 490 μs
  96 ns : highest common frequency between linac – ring
With DR, in order to select arbitrary bucket in MR, have to wait up to ~4.5 ms, even if a bucket in DR was carefully selected
  Power supply can wait only 2 ms, one of only 2798 buckets in 5120 buckets can be selected, may have to change LLRF condition at latter half of linac every pulse
  Can be a big challenge in LLRF precision
ARC
e+ Target
e+ BT (3.5GeV, 0.6nC)
e− Gun
KEKB
Primary e– (3.5GeV, 10nC)
ARC
e+ Target
e+ BT (KEKB: 4GeV, 4nC)
e− Gun
SuperKEKB
Primary e– (3.5GeV, 10nC)
e+ DR (1.1 GeV, 4nC)
96ns
>100ns
>100ns
96ns
DR timing

## Slide 14: Beam Upgrade and Radiation Controls
Step-by-step upgrade of beam limits
  Towards 5 nC per bunch in Phase-3
Beam license applications
  Fall 2013, 10 nA at #28 dump, 1250 nA at #A2 dump
  Spring 2014, New utility rooms, 50 nA at #61 linac-end dump
  Summer 2015, 200 nA at #15 positron target
  Spring 2016, 800 nA at #15 target
  Before Phase-3, 1250 nA at #15 target, 625 nA at #61 dump
Radiation shield additions …
  For Gun, 180deg-arc, Target, Electron stopper, Collimator, Damping-ring dump, Linac-end dump, 5 utility rooms, etc.
Even balancing with PF and PF-AR beam operations
Schedule

## Slide 15
JFY2010
Dismantle KEKB
KEKB operation
SuperKEKB upgrade construction
SuperKEKB operation
Startup, conditioning, etc.
SuperKEKB master schedule
Belle II install,
QCS install
Phase 1
Phase 2、3
・・・
・・・
DR
Phase 1 commissioning：
Basic machine tuning
Low emittance beam tuning
Vacuum scrubbing
Started on Feb.1.2016.
Phase 2 commissioning：
Low beta* tuning at IP
Collision tuning
Start physics data taking
Phase 3：
Physics run with full Belle II with VXD
DR commissioning starts prior to Phase 2
JFY2011
JFY2012
JFY2013
JFY2014
JFY2015
JFY2016
JFY2017
Now (Jun, 2016)
For ~10 years
Akai, Mar.2016.
Large Earthquake
Mar.2011
Phase 1 commissioning goes as expected even with RF-gun

## Slide 16
Construction Schedule
M. Kikuchi
DR schedule

## Slide 17: Linac Schedule Overview
RF-Gun e- beam
commissioning
at A,B-sector
e- commiss.
at A,B,J,C,1
e+ commiss.
at 1,2 sector (FC, DCS, Qe- 50%)
e- commiss.
at 1,2,3,4,5 sector
non damped e+ commiss.
at 1,2, 3,4,5 sectors
e- commiss. at A→5 sectors
damped e+ commiss.
at 1→5 Qe+ = 1~4nC
e- commiss.
at A→5 Qe- = 1~5nC
: Electron
: Positron
: Low current electron
2 nC
Phase2
1 nC
Phase1
Location
↓
Time →
Phase1: high emittance beam for vacuum scrub
Phase2,3: low emittance beam for collision
Schedule
Without Top-up
4 nC
Phase3
Improved RF gun
Direct PF-AR BT
DR Commiss.
Beam Licenses in steps
Low Emittance Beams
4+1 Ring
Injections

## Slide 18: Subjects to Consider
Have to consider too many subjects !
Phronesis needed (Greek: Practical wisdom, Ability to understand the Universal Truth)
Nov.

## Slide 19: Emittance Preservation
Offset injection may solve the issue
Orbit have to be maintained precisely
Mis-alignment should be <0.1mm locally, <0.3mm globally
100 samples
Mis-alignment leads to Emittance blow-up
Sugimoto et al.
Orbit manipulation compensates it
Alignment

## Slide 20: Injector Linac Energy Management
3.5 GeV
10nC x 2 (prim. e-)
5nC x 2 (inj. e-)
1.1 GeV
Damping Ring
circ. 136 m
ECS
BCS
Low emittance
RF gun
e+ target &
LAS capture section
e-/e+ beam with different bunch charge and energy are accelerated by 50 Hz repetition rate.
HER
LER
3T
RF gun
ECS
HER: 7GeV e-
PF: 2.5 GeV e-
LER: 4GeV e+
5 nC x2
1.5 GeV
PF
PF-AR
e+ target
e-
e+
1.1 GeV
4.219 GeV
1.5 GeV
Optics is changed for each pulse by using
pulsed quads (Doublet) & steering magnets
e-/e+ compatible optics
PF-AR: 6.5GeV e-
5nCx1
4 nCx2
0.1nCx1
chicane

## Slide 21
Spares

## Slide 22: Pulse-to-pulse modulation
ARC
e– (2.5GeV, 0.2nC)
e− Gun
ARC
e+ Target
e+ (4GeV, 4nC)
e− Gun
PF Injection
SuperKEKB-LER Injection
e– (3.5GeV, 10nC)
ARC
e– (7GeV, 5nC)
e− Gun
SuperKEKB-HER Injection
ARC
e– (6.5GeV, 5nC)
e− Gun
PF-AR Injection
Damping ring
Event-based Control System
Every 20 ms
F.B
F.B
F.B
F.B
F.B
F.B
F.B
F.B
Four PPM virtual accelerators for SuperKEKB project Based on Dual-tier controls with EPICS and event-system Independent parameter sets for each VA (20ms) >200 parameters for equipment controls many more for beam controls maybe with additional PPM VA of stealth beam for measurement

## Slide 23: Injector Beam Commissioning for Phase-1
Electron beam
  Thermionic gun at the beginning
  1 nC per bunch
  2 bunches per pulse
  50 pulse per second
Positron beam
  Primary electron with 7-8 nC per bunch
  Positron of 0.7 nC at linac end without damping ring

## Slide 24: Progress: RF gun
MR injection from RF gun during Phase-1 was recommended in the last gun review, and was planned for May 2016 since the last year
On May 31, even an unusual centipede (~15cm!!) managed to visit the operation room to celebrate the first injection into HER
Ibaraki Nature Museum
Beam from RF gun

## Slide 25: Beam from RF gun
Successful Injection into MR for the first time, on May.31
And continuing the RF gun operation since Jun.8
Beam from RF gun

## Slide 26: Wire Scanner Measurement
Present beam: 1nC/bunch, 25Hz, 20mm.mrad at the gun, 30~200 mm.mrad at the linac end, ? Energy spread
Phase-2: 2nC/bunch, 50Hz, 20 mm.mrad at the linac end, 0.1% energy spread
Phase-3: 4-5nC/bunch
Much room to enjoy the improvements
Beam from RF gun

## Slide 27: Summary
Injection into SuperKEKB is another challenge with higher beam charge and lower transverse and longitudinal emittance
Steady progress towards designed injection beam in steps
  Alignment: almost confident on the required precision (0.1-mm local, 0.3-mm global), need to maintain for longer term
  Positron generator: another license test, need discharge analysis
  Thermionic gun: re-commissioned for primary electron for positron generation
  RF gun: successful HER injection, following recommendations at review meetings
  Need more radiation shield
  Need much construction left for 2017
Will balance between final beam quality and progressive operation
Will select optimized route depending on available resources
  Negotiation with light sources
  Commissioning and development in parallel (no other choices)
Summary

## Slide 28
SuperKEKB
dual rings
Mt. Tsukuba
600m Injector Linac
PF-AR
PF
Thank you